## Execution Plan
Week | Start Date | End Date | Category | Task/Deliverable | Description/Topic Ideas | Duration (Days) | Priority | Status | Notes
W1 | 2026-01-01 | 2026-01-07 | Website | Website Go-Live | Publish roundlakescommodities.com, verify all pages, SSL | 2 | Critical | Planned | DNS propagation 24-48hrs
W1 | 2026-01-01 | 2026-01-07 | Social Media | LinkedIn Company Page Launch | Create/finalize RLC company page with branding, tagline | 1 | Critical | Planned | Link to founder profile
W1 | 2026-01-01 | 2026-01-07 | Blog Post | Welcome Post: Introducing RLC | Founder story, mission, what to expect from RLC content | 2 | High | Planned | Cornerstone piece
W1 | 2026-01-01 | 2026-01-07 | Thought Leadership | 2026 Commodity Outlook Preview | High-level look ahead at key themes for corn, soy, biofuels | 3 | High | Planned | Timely for new year
W1 | 2026-01-01 | 2026-01-07 | Collateral | Email Signature Template | Branded signature with logo, tagline, website link | 1 | Medium | Planned
W2 | 2026-01-08 | 2026-01-14 | Blog Post | USDA Winter Wheat Seedings Analysis | Analyze USDA Winter Wheat Seedings report (released ~Jan 10) | 2 | High | Planned | Timely with USDA release
W2 | 2026-01-08 | 2026-01-14 | Blog Post | USDA Grain Stocks Commentary | Analysis of quarterly grain stocks report | 2 | High | Planned | Major market mover
W2 | 2026-01-08 | 2026-01-14 | Social Media | Daily LinkedIn Posts (5x) | Share key data points, charts from USDA reports | 5 | Medium | Planned | Engage with discussions
W2 | 2026-01-08 | 2026-01-14 | Website | Power BI Dashboard Embed | Add live market data dashboard to website | 3 | High | Planned | Key differentiator
W3 | 2026-01-15 | 2026-01-21 | Thought Leadership | 2025 Ethanol Year in Review | Comprehensive review of ethanol markets, margins, trends | 4 | High | Planned | Demonstrates expertise
W3 | 2026-01-15 | 2026-01-21 | Blog Post | EIA Weekly Ethanol Update | Analysis of latest production/stocks data | 1 | Medium | Planned | Can become weekly series
W3 | 2026-01-15 | 2026-01-21 | Social Media | Infographic: Ethanol Supply Chain | Visual explainer of corn-to-ethanol process | 2 | Medium | Planned | Educational content
W3 | 2026-01-15 | 2026-01-21 | Outreach | Personal Network Emails | Reach out to 10-15 former colleagues about RLC launch | 2 | High | Planned | Word of mouth
W4 | 2026-01-22 | 2026-01-28 | Thought Leadership | Brazil Soybean Harvest Outlook | Analysis of Brazil's soybean crop, harvest progress, export pace | 4 | High | Planned | Harvest in full swing
W4 | 2026-01-22 | 2026-01-28 | Blog Post | South American Weather Watch | La Nina/El Nino impacts on Safrinha corn planting | 2 | High | Planned | Critical planting period
W4 | 2026-01-22 | 2026-01-28 | Website | Newsletter Signup Implementation | Add email capture form, welcome sequence setup | 2 | High | Planned | Lead generation
W4 | 2026-01-22 | 2026-01-28 | Collateral | Company Brochure Finalization | Finalize 2-page PDF brochure for downloads/sharing | 3 | Medium | Planned
W5 | 2026-01-29 | 2026-02-04 | Blog Post | January WASDE Deep Dive | Comprehensive analysis of monthly WASDE report | 3 | High | Planned | Major monthly event
W5 | 2026-01-29 | 2026-02-04 | Social Media | WASDE Reaction Thread | Real-time LinkedIn commentary on report release | 1 | High | Planned | Demonstrates speed
W5 | 2026-01-29 | 2026-02-04 | Thought Leadership | Understanding USDA Balance Sheets 101 | Educational piece explaining how to read WASDE | 3 | Medium | Planned | Evergreen content
W5 | 2026-01-29 | 2026-02-04 | Website | AI Market Commentary Feature | Launch automated daily market briefings on site | 4 | High | Planned | AI differentiator
W6 | 2026-02-05 | 2026-02-11 | Thought Leadership | Renewable Diesel: The New Frontier | Deep dive on RD growth, SAF mandates, investment trends | 5 | High | Planned | Growing market interest
W6 | 2026-02-05 | 2026-02-11 | Blog Post | Soybean Oil Demand Dynamics | Food vs. fuel demand, crush margins, RD capacity | 2 | High | Planned | Links to biodiesel piece
W6 | 2026-02-05 | 2026-02-11 | Social Media | Poll: Biggest Biofuel Challenge 2026? | Engage audience with interactive poll | 1 | Low | Planned | Engagement driver
W6 | 2026-02-05 | 2026-02-11 | Outreach | Industry Publication Pitch | Pitch guest article to Biofuels Digest or similar | 2 | Medium | Planned | External credibility
W7 | 2026-02-12 | 2026-02-18 | Blog Post | What to Expect at USDA Outlook Forum | Preview of key themes, speakers, data to watch | 2 | High | Planned | Major industry event
W7 | 2026-02-12 | 2026-02-18 | Thought Leadership | Corn Demand Outlook: Feed, Fuel, and Export | Comprehensive demand analysis ahead of forum | 4 | High | Planned | Timely positioning
W7 | 2026-02-12 | 2026-02-18 | Website | Chatbot Beta Launch | Deploy AI chatbot for website visitor Q&A | 5 | Medium | Planned | Tech showcase
W7 | 2026-02-12 | 2026-02-18 | Social Media | Countdown to Outlook Forum | Daily posts building anticipation | 3 | Medium | Planned
W8 | 2026-02-19 | 2026-02-25 | Blog Post | USDA Outlook Forum Live Coverage | Real-time analysis of forum presentations and data | 3 | Critical | Planned | High visibility week
W8 | 2026-02-19 | 2026-02-25 | Thought Leadership | Forum Key Takeaways Report | Comprehensive summary for those who couldn't attend | 3 | High | Planned | Major thought piece
W8 | 2026-02-19 | 2026-02-25 | Social Media | Live-Tweet/Post Forum Sessions | Real-time commentary on LinkedIn | 3 | High | Planned | Shows engagement
W8 | 2026-02-19 | 2026-02-25 | Webinar | Plan First Webinar: March Outlook | Begin planning webinar on spring planting outlook | 2 | Medium | Planned | Target late Feb/early March
W9 | 2026-02-26 | 2026-03-04 | Blog Post | Weekly Export Sales Analysis | Deep dive on USDA export sales and inspections data | 2 | Medium | Planned | Can become weekly feature
W9 | 2026-02-26 | 2026-03-04 | Thought Leadership | China Trade Dynamics 2026 | Analysis of U.S.-China ag trade, policy implications | 4 | High | Planned | Always relevant
W9 | 2026-02-26 | 2026-03-04 | White Paper | Begin: Biofuels 101 Executive Primer | Start drafting comprehensive biofuels guide | 5 | High | Planned | Lead magnet
W9 | 2026-02-26 | 2026-03-04 | Social Media | USDA Export Inspection Charts | Weekly visual data posts | 2 | Medium | Planned
W10 | 2026-03-05 | 2026-03-11 | Blog Post | March WASDE: Pre-Planting Signals | Monthly WASDE analysis with focus on carryout revisions | 3 | High | Planned | Key for spring outlook
W10 | 2026-03-05 | 2026-03-11 | Thought Leadership | Safrinha Corn: Brazil's Second Crop | In-depth on Brazil's safrinha corn planting/outlook | 4 | High | Planned | Safrinha planting underway
W10 | 2026-03-05 | 2026-03-11 | Webinar | Host: Spring Planting Preview Webinar | First RLC webinar on 2026 U.S. planting outlook | 3 | High | Planned | Major milestone
W10 | 2026-03-05 | 2026-03-11 | Social Media | Webinar Promotion Campaign | Daily posts promoting upcoming webinar | 5 | Medium | Planned
W11 | 2026-03-12 | 2026-03-18 | Thought Leadership | Q1 Ethanol Margin Review | Quarterly analysis of ethanol crush margins, trends | 4 | High | Planned | Quarterly flagship piece
W11 | 2026-03-12 | 2026-03-18 | Blog Post | DDGs Market Update | Analysis of distillers grains market, export demand | 2 | Medium | Planned | Niche but valuable
W11 | 2026-03-12 | 2026-03-18 | White Paper | Continue: Biofuels 101 Primer | Continue drafting biofuels primer | 5 | High | Planned
W11 | 2026-03-12 | 2026-03-18 | Website | Client Portal Planning | Begin designing login-protected client area | 3 | Medium | Planned | Future feature
W12 | 2026-03-19 | 2026-03-25 | Blog Post | Prospective Plantings Preview | What to expect from the March 31 USDA report | 2 | High | Planned | Major report preview
W12 | 2026-03-19 | 2026-03-25 | Thought Leadership | Corn vs. Soy: The Planting Decision | Economics driving farmer planting choices | 4 | High | Planned | Timely for planting season
W12 | 2026-03-19 | 2026-03-25 | Social Media | Poll: What Will Farmers Plant? | Engage audience with acreage predictions | 1 | Low | Planned | Engagement
W12 | 2026-03-19 | 2026-03-25 | Outreach | Conference Speaking Applications | Apply to speak at summer/fall conferences | 3 | Medium | Planned | Build pipeline
W13 | 2026-03-26 | 2026-04-01 | Blog Post | USDA Prospective Plantings Deep Dive | Comprehensive analysis of March 31 report | 3 | Critical | Planned | Most important spring report
W13 | 2026-03-26 | 2026-04-01 | Blog Post | USDA Quarterly Stocks Analysis | Same-day stocks report analysis | 2 | High | Planned | Released with plantings
W13 | 2026-03-26 | 2026-04-01 | Social Media | Real-time Plantings Reaction | Live commentary on report release | 1 | High | Planned | Speed matters
W13 | 2026-03-26 | 2026-04-01 | White Paper | Finalize: Biofuels 101 Primer | Complete and design biofuels white paper | 3 | High | Planned | Launch as lead magnet
W14 | 2026-04-02 | 2026-04-08 | Blog Post | Weekly Planting Progress Tracker | First weekly update on U.S. corn/soy planting | 2 | High | Planned | Weekly series through May
W14 | 2026-04-02 | 2026-04-08 | Thought Leadership | Weather Impact on Spring Planting | Analysis of early season weather patterns | 3 | High | Planned | Weather critical now
W14 | 2026-04-02 | 2026-04-08 | Website | White Paper Landing Page Live | Launch Biofuels 101 download with email capture | 2 | High | Planned | Lead generation active
W14 | 2026-04-02 | 2026-04-08 | Social Media | Daily Planting Updates | Brief daily posts on planting conditions | 5 | Medium | Planned
W15 | 2026-04-09 | 2026-04-15 | Blog Post | April WASDE: First New-Crop Look | First official new-crop balance sheet numbers | 3 | High | Planned | Major monthly report
W15 | 2026-04-09 | 2026-04-15 | Blog Post | Planting Progress Week 2 | Continued weekly planting tracker | 2 | High | Planned | Weekly series
W15 | 2026-04-09 | 2026-04-15 | Thought Leadership | Fertilizer Costs and Farm Margins 2026 | Input cost analysis affecting planting decisions | 3 | Medium | Planned | Producer-focused
W15 | 2026-04-09 | 2026-04-15 | Webinar | Plan: Q2 Market Outlook Webinar | Begin planning April/May webinar | 2 | Medium | Planned
W16 | 2026-04-16 | 2026-04-22 | Thought Leadership | Brazil Soybean Harvest Final Report | Wrap-up of Brazil's record soybean harvest | 4 | High | Planned | Harvest winding down
W16 | 2026-04-16 | 2026-04-22 | Blog Post | Planting Progress Week 3 | Weekly planting update | 2 | High | Planned
W16 | 2026-04-16 | 2026-04-22 | Social Media | Brazil Harvest Infographic | Visual summary of Brazil's crop | 2 | Medium | Planned
W16 | 2026-04-16 | 2026-04-22 | Case Study | Begin First Case Study Draft | Start documenting early client success if available | 3 | Medium | Planned
W17 | 2026-04-23 | 2026-04-29 | Thought Leadership | EPA RFS Update: What It Means for Markets | Analysis of renewable fuel standard implications | 4 | High | Planned | Policy timing varies
W17 | 2026-04-23 | 2026-04-29 | Blog Post | Planting Progress Week 4 | Weekly planting tracker | 2 | High | Planned
W17 | 2026-04-23 | 2026-04-29 | Blog Post | Corn Planting Window Analysis | Optimal planting dates, yield implications | 2 | Medium | Planned | Agronomic focus
W17 | 2026-04-23 | 2026-04-29 | Webinar | Host: Q2 Market Outlook Webinar | Second quarterly webinar | 3 | High | Planned
W18 | 2026-04-30 | 2026-05-06 | Blog Post | May WASDE: Old-Crop Tightening? | Monthly WASDE with focus on old-crop stocks | 3 | High | Planned
W18 | 2026-04-30 | 2026-05-06 | Blog Post | Planting Progress Week 5 | Weekly planting update | 2 | High | Planned
W18 | 2026-04-30 | 2026-05-06 | Thought Leadership | Safrinha Corn Development Update | Brazil second-crop corn progress | 3 | High | Planned | Critical growth period
W18 | 2026-04-30 | 2026-05-06 | Social Media | Weekly Export Charts | Visual export sales data | 2 | Medium | Planned
W19 | 2026-05-07 | 2026-05-13 | Blog Post | Planting Progress Week 6 | Weekly planting tracker | 2 | High | Planned
W19 | 2026-05-07 | 2026-05-13 | Thought Leadership | Early Season Crop Conditions | First emergence/condition reports analysis | 3 | Medium | Planned | Conditions start now
W19 | 2026-05-07 | 2026-05-13 | Newsletter | Launch Monthly Email Newsletter | First issue to subscriber list | 3 | High | Planned | Build engagement
W19 | 2026-05-07 | 2026-05-13 | Outreach | Podcast Guest Pitch | Pitch founder as guest on commodity podcasts | 2 | Medium | Planned
W20 | 2026-05-14 | 2026-05-20 | Blog Post | Planting Progress Week 7 | Weekly planting update | 2 | High | Planned
W20 | 2026-05-14 | 2026-05-20 | Thought Leadership | Corn vs. Soy: Planted Acres Analysis | Compare plantings to intentions, implications | 4 | High | Planned
W20 | 2026-05-14 | 2026-05-20 | Social Media | Planting Progress Maps | Visual state-by-state progress | 2 | Medium | Planned
W20 | 2026-05-14 | 2026-05-20 | White Paper | Begin: Hedging Strategies Guide | Start new lead magnet on risk management | 4 | Medium | Planned
W21 | 2026-05-21 | 2026-05-27 | Blog Post | Final Planting Progress Report | Wrap-up of planting season | 2 | High | Planned | Season complete
W21 | 2026-05-21 | 2026-05-27 | Thought Leadership | U.S. Corn & Soy: Post-Plant Outlook | Initial yield expectations, weather outlook | 4 | High | Planned
W21 | 2026-05-21 | 2026-05-27 | Blog Post | Memorial Day Weekend: Ag Market Impacts | Historical holiday trading patterns | 2 | Low | Planned | Light content week
W22 | 2026-05-28 | 2026-06-03 | Blog Post | Weekly Crop Conditions Tracker | First detailed conditions analysis | 2 | High | Planned | Weekly series begins
W22 | 2026-05-28 | 2026-06-03 | Thought Leadership | Brazil Safrinha Corn: Final Forecast | End-of-season Brazil corn outlook | 4 | High | Planned | Harvest approaching
W22 | 2026-05-28 | 2026-06-03 | Social Media | Crop Conditions Charts | Visual weekly conditions data | 2 | Medium | Planned
W22 | 2026-05-28 | 2026-06-03 | White Paper | Continue: Hedging Strategies Guide | Continue drafting | 4 | Medium | Planned
W23 | 2026-06-04 | 2026-06-10 | Blog Post | June WASDE: Growing Season Begins | Monthly WASDE analysis | 3 | High | Planned
W23 | 2026-06-04 | 2026-06-10 | Blog Post | Crop Conditions Week 2 | Weekly conditions tracker | 2 | High | Planned
W23 | 2026-06-04 | 2026-06-10 | Thought Leadership | Ethanol Summer Driving Season Outlook | Seasonal demand analysis | 3 | High | Planned | Summer blend deadline
W23 | 2026-06-04 | 2026-06-10 | Webinar | Plan: Summer Crop Webinar | Plan mid-summer crop outlook webinar | 2 | Medium | Planned
W24 | 2026-06-11 | 2026-06-17 | Blog Post | Crop Conditions Week 3 | Weekly conditions tracker | 2 | High | Planned
W24 | 2026-06-11 | 2026-06-17 | Thought Leadership | Weather Markets: June Heat Concerns | Weather pattern analysis for crops | 4 | High | Planned | Weather premium season
W24 | 2026-06-11 | 2026-06-17 | Social Media | Daily Weather Updates | Brief weather/crop posts | 5 | Medium | Planned
W24 | 2026-06-11 | 2026-06-17 | Client | Mid-Year Client Check-ins | Touch base with existing clients | 3 | High | Planned | Relationship building
W25 | 2026-06-18 | 2026-06-24 | Blog Post | June Acreage Report Preview | What to expect from USDA acreage | 2 | High | Planned | Major report coming
W25 | 2026-06-18 | 2026-06-24 | Blog Post | Crop Conditions Week 4 | Weekly conditions tracker | 2 | High | Planned
W25 | 2026-06-18 | 2026-06-24 | Thought Leadership | Acreage Shifts: Corn, Soy, Cotton, Wheat | Multi-crop acreage analysis preview | 4 | High | Planned
W25 | 2026-06-18 | 2026-06-24 | White Paper | Finalize: Hedging Strategies Guide | Complete second white paper | 3 | High | Planned
W26 | 2026-06-25 | 2026-07-01 | Blog Post | USDA Acreage Report Deep Dive | Comprehensive June 30 acreage analysis | 3 | Critical | Planned | Most important summer report
W26 | 2026-06-25 | 2026-07-01 | Blog Post | Quarterly Stocks Analysis | Same-day stocks report analysis | 2 | High | Planned
W26 | 2026-06-25 | 2026-07-01 | Thought Leadership | Q2 2026 Commodity Market Review | Comprehensive quarterly review | 5 | High | Planned | Quarterly flagship
W26 | 2026-06-25 | 2026-07-01 | Social Media | Real-time Acreage Reaction | Live commentary on report | 1 | High | Planned

## Gantt Chart
Task | Category | Start | Days | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
Website Go-Live | Website | 2026-01-01 | 2
LinkedIn Launch | Social Media | 2026-01-01 | 1
Welcome Post: Introducing RLC | Blog Post | 2026-01-01 | 2
2026 Commodity Outlook Preview | Thought Leadership | 2026-01-01 | 3
Power BI Dashboard Embed | Website | 2026-01-08 | 3
USDA Winter Wheat/Stocks Analysis | Blog Post | 2026-01-08 | 4
2025 Ethanol Year in Review | Thought Leadership | 2026-01-15 | 4
Brazil Soybean Harvest Outlook | Thought Leadership | 2026-01-22 | 4
Newsletter Signup Implementation | Website | 2026-01-22 | 2
January WASDE Deep Dive | Blog Post | 2026-01-29 | 3
AI Market Commentary Feature | Website | 2026-01-29 | 4
Renewable Diesel: The New Frontier | Thought Leadership | 2026-02-05 | 5
USDA Outlook Forum Preview | Blog Post | 2026-02-12 | 2
Chatbot Beta Launch | Website | 2026-02-12 | 5
USDA Outlook Forum Coverage | Blog Post | 2026-02-19 | 3
Forum Key Takeaways Report | Thought Leadership | 2026-02-19 | 3
Biofuels 101 White Paper (Start) | White Paper | 2026-02-26 | 21
China Trade Dynamics 2026 | Thought Leadership | 2026-02-26 | 4
Spring Planting Preview Webinar | Webinar | 2026-03-05 | 3
Safrinha Corn: Brazil Second Crop | Thought Leadership | 2026-03-05 | 4
Q1 Ethanol Margin Review | Thought Leadership | 2026-03-12 | 4
Prospective Plantings Preview | Blog Post | 2026-03-19 | 2
Corn vs. Soy: Planting Decision | Thought Leadership | 2026-03-19 | 4
USDA Prospective Plantings Analysis | Blog Post | 2026-03-26 | 3
Biofuels 101 White Paper Launch | White Paper | 2026-03-26 | 3
Weekly Planting Progress Series | Blog Post | 2026-04-02 | 56
Weather Impact on Planting | Thought Leadership | 2026-04-02 | 3
April WASDE Analysis | Blog Post | 2026-04-09 | 3
Brazil Soybean Harvest Wrap-Up | Thought Leadership | 2026-04-16 | 4
EPA RFS Analysis | Thought Leadership | 2026-04-23 | 4
Q2 Market Outlook Webinar | Webinar | 2026-04-23 | 3
Safrinha Corn Development | Thought Leadership | 2026-04-30 | 3
Monthly Email Newsletter Launch | Newsletter | 2026-05-07 | 3
Hedging Strategies Guide (Start) | White Paper | 2026-05-14 | 35
U.S. Post-Plant Outlook | Thought Leadership | 2026-05-21 | 4
Weekly Crop Conditions Series | Blog Post | 2026-05-28 | 35
Brazil Safrinha Final Forecast | Thought Leadership | 2026-05-28 | 4
Ethanol Summer Season Outlook | Thought Leadership | 2026-06-04 | 3
Weather Markets Analysis | Thought Leadership | 2026-06-11 | 4
June Acreage Report Preview | Blog Post | 2026-06-18 | 2
Hedging Strategies Guide Launch | White Paper | 2026-06-18 | 3
USDA Acreage Report Deep Dive | Blog Post | 2026-06-25 | 3
Q2 Commodity Market Review | Thought Leadership | 2026-06-25 | 5

## Content Calendar
Month | Week | Blog Posts | Thought Leadership | Webinars | White Papers | Key USDA/Market Events | Seasonal Context
January | W1-W2 | Welcome Post, USDA Reports Analysis | 2026 Outlook Preview | - | - | Winter Wheat Seedings, Grain Stocks | South America harvest begins
January | W3-W4 | EIA Ethanol Update, Brazil Weather | Ethanol Year Review, Brazil Soy Outlook | - | - | January WASDE | Brazil soy harvest, safrinha planting
February | W5-W6 | WASDE Analysis, Soybean Oil Demand | WASDE 101 Guide, Renewable Diesel Deep Dive | - | - | February WASDE | Pre-USDA Outlook Forum
February | W7-W8 | Outlook Forum Preview & Coverage | Forum Key Takeaways, Corn Demand Outlook | - | - | USDA Outlook Forum (~Feb 20) | Major industry event
March | W9-W10 | Export Sales, March WASDE | China Trade, Safrinha Corn Analysis | Spring Planting Preview | Biofuels 101 (start) | March WASDE, Export Sales | Brazil safrinha critical
March | W11-W12 | DDGs Market, Plantings Preview | Q1 Ethanol Review, Corn vs. Soy Economics | - | Biofuels 101 (continue) | Pre-Prospective Plantings | Pre-planting analysis
March/April | W13-W14 | Prospective Plantings, Planting Tracker | Weather/Planting Analysis | - | Biofuels 101 (launch) | Prospective Plantings (Mar 31) | U.S. planting begins
April | W15-W16 | April WASDE, Weekly Planting | Fertilizer Costs, Brazil Harvest Wrap | - | - | April WASDE | Peak planting season
April | W17-W18 | Weekly Planting, May WASDE | EPA RFS Analysis, Safrinha Update | Q2 Market Outlook | - | May WASDE, EPA RFS | Planting continues
May | W19-W20 | Weekly Planting, Crop Conditions | Early Season Conditions | - | Hedging Guide (start) | - | Emergence begins
May | W21-W22 | Final Planting Report, Conditions | Post-Plant Outlook, Brazil Safrinha Final | - | Hedging Guide (continue) | - | Planting complete, growing season
June | W23-W24 | June WASDE, Weekly Conditions | Ethanol Summer Outlook, Weather Markets | - | Hedging Guide (continue) | June WASDE | Critical crop development
June | W25-W26 | Acreage Preview, Acreage Deep Dive | Multi-Crop Acreage, Q2 Review | - | Hedging Guide (launch) | Acreage & Stocks (Jun 30) | Weather premium season

## Metrics Tracker
Metric | Target (Q1) | Target (Q2) | Actual (Q1) | Actual (Q2) | Notes
Website Traffic (monthly visitors) | 500 | 2000 |  |  | Track via Google Analytics
LinkedIn Followers | 250 | 750 |  |  | Company page followers
LinkedIn Post Engagement Rate | 5% | 7% |  |  | Likes + Comments / Followers
Email Newsletter Subscribers | 50 | 200 |  |  | Mailchimp or similar
Blog Posts Published | 12 | 24 |  |  | Target 2-4/month
Thought Leadership Pieces | 8 | 16 |  |  | In-depth articles
Webinars Hosted | 1 | 3 |  |  | Quarterly minimum
Webinar Attendees (avg) | 15 | 30 |  |  | Growing each session
White Papers Published | 1 | 2 |  |  | Lead magnets
White Paper Downloads | 25 | 100 |  |  | Email captures
Inbound Leads (via website) | 3 | 10 |  |  | Contact form submissions
Consultation Requests | 2 | 8 |  |  | Free consultation signups
Media Mentions/Guest Posts | 1 | 3 |  |  | External publications
Podcast Appearances | 0 | 2 |  |  | Guest on industry podcasts
Client Conversions | 1 | 3 |  |  | Paying clients acquired

## Content Ideas Bank
Category | Title/Topic | Description | Best Timing | Target Audience | Status
Thought Leadership | Why Wall Street Analytics Matter for Agriculture | Founder's perspective on bringing institutional-grade analysis to ag markets | Launch/Anytime | All audiences | Planned
Thought Leadership | The Hidden Costs of Free Market Data | Comparison of free vs. premium data sources, value of aggregation | Anytime | Producers, Investors | Idea
Thought Leadership | AI in Commodity Markets: Reality vs. Hype | How RLC uses AI practically, not just buzzwords | Q1-Q2 | Tech-forward clients | Idea
Blog Post | How to Read a USDA WASDE Report | Step-by-step guide for beginners | Evergreen | Producers, New traders | Planned
Blog Post | Crush Margins Explained: Soybean and Corn | Educational piece on margin calculations | Evergreen | All audiences | Idea
Blog Post | Export Inspections vs. Export Sales: What's the Difference? | Educational on USDA export data | Evergreen | Traders, Analysts | Idea
Blog Post | La Nina and South American Crops | Weather pattern impacts on Brazil/Argentina | Oct-Feb | Traders, Producers | Idea
Blog Post | Understanding Ethanol RINs and D-Codes | Regulatory explainer | Evergreen | Biofuel investors | Idea
Blog Post | Basis Explained: Why Local Prices Differ from Futures | Producer-focused educational | Harvest season | Producers | Idea
Webinar | Hedging 101 for Corn and Soy Producers | Interactive workshop on risk management basics | Pre-planting or Post-harvest | Producers | Idea
Webinar | Biofuel Investment Landscape 2026 | Market overview for investors | Q2 | Investors | Idea
Webinar | Reading the Commodity Markets: A Trader's Perspective | Technical analysis and market structure | Anytime | Traders, Analysts | Idea
White Paper | AgTech Investment Trends 2026 | Overview of technology investments in agriculture | Q3-Q4 | Investors | Idea
White Paper | Carbon Markets and Agriculture | Emerging carbon credit opportunities for farmers | Q2-Q3 | Producers, Investors | Idea
White Paper | South American Agriculture: A Complete Guide | Comprehensive overview of Brazil/Argentina ag | Q1 (pre-harvest) | All audiences | Idea
Case Study | How a Midwest Farmer Used Hedging to Lock In Profits | Success story (real or composite) | Post-harvest | Producers | Idea
Case Study | Ethanol Plant Feedstock Cost Management | How an ethanol producer optimized corn buying | Anytime | Buyers, Producers | Idea
Infographic | U.S. Corn Usage Breakdown | Visual pie chart of feed/fuel/export/food | Evergreen | All audiences | Idea
Infographic | Global Soybean Trade Flows | Map showing major exporters/importers | Evergreen | All audiences | Idea
Infographic | Ethanol Production Process | Visual corn-to-ethanol explainer | Evergreen | All audiences | Idea
Video/Short | 60-Second Market Update | Quick daily video format for social | Daily | All audiences | Idea
Video/Short | This Week in Ag Markets | Weekly 2-3 minute recap video | Weekly | All audiences | Idea
Newsletter | Weekly Commodity Digest | Email roundup of the week's key developments | Weekly | Subscribers | Planned
Newsletter | Monthly Market Outlook | Deeper monthly analysis email | Monthly | Subscribers | Idea
Podcast | Commodity Conversations (RLC Podcast) | Interview series with industry experts | Q3+ | All audiences | Future idea